Khalifa University (KU), as a leading research institution in the region, will serve as the central hub for the system integration, assembly, and initial validation of the Na-ion BESS units. Utilizing KU’s advanced research facilities and multidisciplinary engineering team, Khalifa University will lead the system-level integration, transforming UNIGRID's core cell and pack technology into two fully functional, field-ready BESS prototypes for validation by ACWA Power. Our team, comprising two Postdoctoral Fellows, one Research Engineer, and one PhD student, with expertise in BMS, control systems, and hardware level integration, will work on building and testing the prototype under the supervision of the project lead of Professor Mohamed El Moursi.

Subtask 1.2: Khalifa University to build a Cabinet-style unit

Upon receiving the 40 x 16S1P Na-ion battery packs and associated technical documentation from UNIGRID, the Khalifa University team will undertake the complete integration, assembly, and prototype-level testing of the two 150 kWh BESS cabinets. KU tasks are subdivided into the following subtasks:

### Task Breakdown for Khalifa University: BESS Prototype Integration

Subtask 1.2.0: Detailed Engineering, Component Selection, and BOM Finalization

This initial phase translates the project's high-level requirements into a concrete, buildable design and a list of procurable components.

- Engineering Analysis:

  - The KU team will analyze all technical data provided by UNIGRID (thermal, electrical, mechanical).

  - Perform necessary calculations for thermal load dissipation, electrical system sizing (voltage/current), and structural weight distribution.

- Component Selection & Specification:

  - Mechanical Selection: Research and specify the exact commercial cabinet model, the required cabinet, and all internal mounting hardware.

  - Electrical Selection: Research and specify the exact models for inverter, DC contactors, high-speed fuses, circuit breakers, and all high-voltage cabling that meet the system's performance and safety requirements.

  - Control & Safety Selection: Specify the exact models for the BESS Controller (PLC), HMI touchscreen, smoke/off-gas sensors If needed.

- Bill of Materials (BOM) Generation:

  - Compile all selected components into a single, comprehensive Bill of Materials (BOM), complete with manufacturer names, part numbers, and quantities.

- Handover for Procurement: Deliver the finalized BOM to YAS Energy to initiate the procurement process. The KU project timeline for assembly will commence upon the complete delivery of all items on this BOM.

Deliverable: A complete and final Bill of Materials (BOM) for two BESS prototypes, submitted to YAS Energy.

#### Subtask 1.2.1: Structural & Mechanical Assembly

(This phase begins upon receipt of the procured cabinet and hardware)

- Physical Assembly: Upon delivery of the procured commercial cabinets, the team will:

  - Install the custom internal racking system.

  - Securely mount all major components: UNIGRID battery packs, the PCS inverter, the main DC protection box, HVAC unit, and control panel.

Deliverable: Two physically assembled BESS cabinets with all major hardware securely installed.

#### Subtask 1.2.2. Electrical System Integration

This phase involves the complete electrical wiring of DC and AC power paths.

- Assemble High-Voltage DC Architecture: The team will design the series connection for the 15 battery packs to achieve the target DC bus voltage for the inverter.

- Develop Electrical Schematics: Comprehensive electrical schematics will be created, detailing the complete wiring plan.

- Integrate Protection Devices: All DC and AC protection devices (fuses, circuit breakers, contactors) will be physically installed and wired into the power path as per the schematics.

- Initial Electrical Verification: Perform preliminary, unpowered tests, including point-to-point continuity checks and insulation resistance testing, to verify connections.

#### Subtask 1.2.3. Control, Software, and Communication Integration

This phase focuses on the software and communication networks that enable the BESS to operate automatically and safely.

- Program the BESS Controller (EMS): A central BESS controller will be programmed with the core operating logic, including a state machine for managing Idle, Charging, Discharging, and Fault states.

- Implement Inverter Control: The controller will be programmed to send precise commands to the inverter, translating high-level requests (e.g., "discharge at 100 kW") to control active and reactive power.

- Create Local HMI: The on-cabinet touchscreen (HMI) can be programmed to provide a user-friendly local interface for diagnostics, manual control, and viewing of key system parameters.

Deliverables:

- Operational BESS controller with fully integrated BMS and inverter communication.

#### Subtask 1.2.4. System Safety, Testing, and Final Handover

This final integration phase focuses on safety systems and performing rigorous in-house testing to ensure the prototypes are ready for field deployment.

- Integrate Safety & Thermal Systems:

  - Wire the Emergency Stop (E-Stop) circuit to directly control the main contactors and provide a shutdown signal to the inverter.

- Conduct Power-Up: A systematic, staged power-up sequence will be performed to safely energize the system for the first time, verifying all subsystems are functioning as expected.

- Perform Charge discharge and grid tests:

  - Verifying successful communication with the inverter.

  - Conducting low-power charge/discharge cycles using the DC electronic load to confirm basic functionality.

  - Conducting full-power charge/discharge cycles with a grid and AC load in a grid mode.

  - Generating a test report results for each unit.

Deliverables:

- A complete, documented test report for each BESS unit.

- Two fully assembled, and validated BESS prototypes, ready for handover to YAS Energy for transport to the ACWA Power test site.

Proposed Project Schedule by KU

| Milestones |  |
| --- | --- |
| Quarters | 1 | 2 | 3 | 4 | 5 |
| Task 1: BESS Cell, Pack and System build out |  |  |  |  |  |
| 1.1 UNIGRID Cell & Pack build, shipping to Khalifa University |  |  |  |  |  |
| 1.2 Khalifa University |  |  |  |  |  |
| Subtask 1.2.0: Detailed Engineering, Component Selection, and BOM Finalization |  |  |  |  |  |
| #### Subtask 1.2.1: Structural & Mechanical Assembly |  |  |  |  |  |
| #### Subtask 1.2.2-4. Integration, Testing, and Final Handover |  |  |  |  |  |
| Phase 2. Unit Delivery by YAS Energy, installation and Operation by ACWA Power |  |  |  |  |  |

To ensure an efficient and streamlined execution of Task 1, Khalifa University will first conduct a detailed engineering review and will then provide YAS Energy with a comprehensive Bill of Materials (BOM). This procurement list will specify all required third-party components for the two complete BESS prototypes, including the selected inverters, the outdoor-rated cabinets, BMS interface hardware, switchgear, and all necessary control and safety systems. Khalifa University requires two quarters (six months) to complete the full assembly, integration, and testing of both units. Critically, this six-month assembly and testing timeline will officially commence only after YAS Energy has confirmed the complete delivery of all components specified in the BOM to our facilities. This delivery-dependent start date is essential to guarantee an uninterrupted workflow, mitigate risks associated with supply chain delays, and allow our team to proceed with the build-out on a firm and predictable schedule.

## KU Requirements from YAS-ENERGY:

This section outlines the preliminary list of major components required for the assembly of the two 150 kWh Sodium-Ion BESS prototypes. This list is provided to facilitate initial budgetary planning and to identify long-lead-time items for early sourcing.

A final, detailed Bill of Materials (BOM) with specific manufacturer part numbers will be delivered within one month of the official project start date, following the completion of our detailed engineering review and UNIGRID's data submission.

Tentative Component List for Procurement by YAS Energy

| No. | Component Category | Key Specifications & Requirements |
| --- | --- | --- |
| 1 | Grid-Tie Inverter (Quantity: 2) | - Type: Bidirectional (4-quadrant) battery inverter. - Power Rating: Minimum 100 kW continuous at ambient temperature of 50°C. - DC Input Voltage: Nominally 480-850 Vdc (Final range to be confirmed). - AC Output: 400 Vac (configurable), 3-Phase + Neutral, 50/60 Hz. - Communication: Modbus TCP and/or CAN bus; IEC 61850 capability. - Key Features: - Grid-forming capability. - Full suite of ancillary services (VAR control, frequency regulation). - Programmable parameters and accessible API. Integrated protections (Anti-islanding, OVP/UVP, etc.). |
| 2 | BESS Enclosure Cabinet (Quantity: 2) | - Type: Outdoor-rated, modular, double-walled cabinet with insulation. - IP Rating: Minimum IP55 - Material: Corrosion-resistant construction (e.g., powder-coated galvanized steel). - Mechanical Features: Integrated forklift pockets and certified lifting hooks. - Thermal Management: o Primary: Integrated, closed-loop cabinet HVAC / Air Conditioner unit. o Secondary: Internal air circulation fans for even temperature distribution. |
| 3 | DC Power Components (Lot for 2 units) | - DC Busbars: Tinned copper, rated for >400A continuous. - DC Switchgear: - Main DC contactors (positive, negative, pre-charge) rated for 1000 Vdc. - High-speed DC fuses for battery string protection. o Lockable, manual DC service disconnect switch - Cabling & Connectors: 1000V-rated flexible DC power cables and correctly sized terminal lugs. |
| 4 | Control, Monitoring & Safety Systems (Lot for 2 units) | - BESS Controller (EMS): Industrial-grade PLC or embedded computer. - Human-Machine Interface (HMI): ≥10-inch industrial, sunlight-readable touchscreen - Fire Detection: Aspirating smoke detector and/or off-gas sensor.• Fire Suppression: Pre-engineered, automated clean agent system (e.g., Novec™ 1230). - Safety Peripherals: E-Stop buttons, visual/audible alarms., Networking: Industrial Ethernet switch. |
| 5 | Essential Testing Equipment | - Programmable DC Electronic Load: - Requirement: Procure one unit for project duration. - Specification: ≥100 kW, regenerative capability preferred, compatible with 480-850 Vdc range. |
| 6 | Miscellaneous & Integration Support | Integration Fund: A pre-approved petty cash fund/budget for the immediate purchase of minor components (relays, fasteners, etc.) during assembly to prevent delays. |

### Khalifa University Team: Roles and Responsibilities(Optional)

| Personnel | Primary Role | Role Description | Key Responsibilities |
| --- | --- | --- | --- |
| Dr. Nirmal and Muhammad Noman | Lead, Power Electronics & Grid Integration | Oversees the entire power conversion and grid integration aspects. Leads the design, selection, and integration of the Power Conversion System (PCS) and ensures compliance with electrical standards. | • Inverter/PCS and DC-DC converter selection(optional), sizing, and procurement specifications. • Design of electrical interconnections, protection schemes, and grounding. • Coordination with grid integration requirements for ACWA Power. • Oversee electrical safety aspects and compliance. |
| Dr. Ammar | Battery System Integration Lead | Focuses on the safe and efficient integration of the Na-ion battery packs with the overall system, including BMS communication. | • Design and optimization of battery pack layout and physical integration within the cabinet • Integration and validation of UNIGRID's BMS with the master system controller. • Responsible for battery safety protocols within the system. |
| Saikrishna | Mechanical Design & Assembly Lead | Leads the structural and mechanical aspects, ensuring physical robustness, proper assembly, and adherence to minimum standards required for testing at KU-APEC labs. | • Management of the procurement of the commercial cabinet. • Design of custom internal mounting structures (racks, plates). • Leads the physical assembly and component mounting. • Provides mechanical support for all component integration. |
| Dr. Ammar and Muhammad Noman | Control System & Data Acquisition | Develops and integrates the master control system (EMS), Human-Machine Interface (HMI), and data logging infrastructure, ensuring seamless communication between all components. | • Design and implementation of communication protocols (Modbus, CAN bus) for all integrated devices. • Development of the HMI and local control interfaces. • Design and implementation of the data acquisition, logging, and remote monitoring systems. • Support for system-level testing and data analysis. |

KU Questions and Inquiries for UNIGRID:

To facilitate a smooth and efficient system integration process for the Na-ion BESS prototypes, we have compiled a list of required technical data and questions.

1. Electrical Performance

- Voltage Characteristics:

  - Please provide the detailed State of Charge (SoC) vs. Open Circuit Voltage (OCV) curve data for the prismatic cell and the 16S1P pack, preferably in a tabular format.

  - What is the full operational DC voltage window of the pack (from 0% to 100% SoC)? This is essential for selecting a compatible inverter and determining if a DC-DC converter stage is necessary to meet ACWA Power's grid requirements.

- Charging/Discharging Profiles:

  - What are the recommended Constant Current / Constant Voltage (CC-CV) charging profiles? Please specify C-rates, voltage setpoints, and termination current.

  - What are the maximum continuous and peak (e.g., 10s, 60s) charge and discharge current/power ratings for the pack?

- Efficiency & Impedance:

  - Can you provide data on the pack's DC internal resistance (or impedance) across various states of charge and temperatures? This is crucial for our efficiency modeling.

- Ripple Current Tolerance:

  - What is the maximum DC ripple current the battery pack can tolerate from an inverter without affecting performance or lifespan?

- Fault Current:

  - What is the maximum short-circuit fault current the pack can deliver, and for how long before the BMS protection trips?

2. Thermal Management System Design

- Operating Limits:

  - What is the defined operational temperature range (min/max) for the pack?

  - What is the optimal temperature range for maximizing cycle life and performance?

- Heat Generation:

  - Please provide data on the heat generation (preferably in Watts) of a single pack during continuous charge and discharge at various C-rates (e.g., C/3, C/2, 1C).

- Airflow Requirements:

  - What is the recommended volumetric airflow (in CFM or m³/h) per pack required to keep it within the optimal temperature range during continuous 1C operation at a 45°C ambient temperature?

- Sensor Data:

  - Where are the temperature sensors located within the pack? Are there known or anticipated hot spots that our cooling design should target?

- Smoke detector, inside the cabinet, is needed or not? Is smoke toxic?

3. Mechanical & Physical Integration

- Physical Specifications:

  - Please provide detailed 3D CAD models (in STEP or IGES format) and 2D mechanical drawings of the 16S1P pack.

- Mounting & Connections:

  - Please provide specifications for all mounting points (e.g., location, bolt size, torque requirements).

  - What are the dimensions and specifications for the main DC power terminals? Please recommend a suitable cable lug size.

  - Where is the physical location of the communication port on the pack?

4. Safety & Certification Documentation

- Test Reports:

  - As per the proposal, please provide the full test reports for UL9540A, UL1973, and UN38.3. The UL9540A report is especially critical for our system-level fire safety and suppression design.

- Safety Data:

  - Please provide the complete Safety Data Sheet (SDS) for the cells and packs.

  - What are the exact BMS safety setpoints for over/under-voltage, over-current, and over/under-temperature?

- What is the recommended State of Charge (SoC) for shipping and for short-term storage prior to integration?

5. System Safety, Failure Analysis, and Risk Assessment

  - Venting & Gas Composition:

    - In a thermal runaway event, does the pack have a designed vent? If so, where is it located, in what direction does it vent, and what is the chemical composition of the vented gas? This is critical for cabinet design.

    - Is fume extraction unit is needed in case of damage to battery cells? If so, what is the recommended fume extraction capacity need to be installed?

  - Fire Suppression:

    - Beyond the UL9540A report, what is the recommended fire suppression agent (e.g., Novec 1230, CO2, water mist, etc.) for this specific cell chemistry? Are there any agents that should not be used?

    - Unigrid would suggest KU on the fire extinguishment or suppression type to be used for operation.

  - In the case of an unforeseen event of failure of one of the components of test setup, such as, battery management system, controller, power electronics circuits, or protection system, provide a comprehensive list of hazards that need to be taken care of for risk assessment.

    - Electrical hazards?

    - Chemical hazards?

    - Explosion risk?

  - Cascading Failure Prevention:

    - What design features are incorporated into the pack to prevent a single cell failure from cascading to adjacent cells?

Check full cpactiy

Check the automation

3 cycles charge discharge